## Project Plan
| Special Events | Start | End |  | Project Plan Template
Time off
| Holiday |  |  |  | 2022-05-04 | [27 empty] | 2022-06-01 | [29 empty] | 2022-07-01 | [30 empty] | 2022-08-01 | [30 empty] | 2022-09-01 | [29 empty] | 2022-10-01 | [30 empty] | 2022-11-01
 | time axis 2022-05-04 to 2022-11-15
|  | Start | End | % Compl.
Project |  | 2022-05-04 | 2022-06-05
Study |  | 2022-05-04 | 2022-05-06
| First Meeting | 2022-05-04 | 2022-05-04
| FDS Document | 2022-05-04 | 2022-05-04
| P&I Diagram Standardization | 2022-05-04 | 2022-05-04
| Master I/O List | 2022-05-05 | 2022-05-06
| Equipment Module/Control Module / Phase Identification | 2022-05-05 | 2022-05-06
Documentation - |  | 2022-05-04 | 2022-05-04
| FDS | 2022-05-04 | 2022-05-04
Standardisation |  | 2022-05-04 | 2022-05-04
| Nomenclature - ( Controller Program ) | 2022-05-04 | 2022-05-04
| Master I/O List Preparation | 2022-05-04 | 2022-05-04
| FDS | 2022-05-04 | 2022-05-04
| Hardware | 2022-05-04 | 2022-05-04
Documentation - Phase / Equipment/ Control Module *1 |  | 2022-05-04 | 2022-05-04
| Sample Development Document- Control Module | 2022-05-04 | 2022-05-04
| Sample Test Document - Control Module | 2022-05-04 | 2022-05-04
Controller Program |  | 2022-05-05 | 2022-06-05
AOI |  | 2022-05-05 | 2022-05-17
| AOI-Analog Input | 2022-05-05 | 2022-05-06
| AOI-Analog Output | 2022-05-09 | 2022-05-10
| AOI-Soft Alarm | 2022-05-11 | 2022-05-11
| AOI-Alarm AOI | 2022-05-12 | 2022-05-12
| AOI-PID AOI | 2022-05-13 | 2022-05-13
| AOI-Pump | 2022-05-16 | 2022-05-16
| AOI-VentFilter | 2022-05-17 | 2022-05-17
| AOI-xxxxx | 2022-05-05 | 2022-05-05
| AOI-xxxxx | 2022-05-05 | 2022-05-05
| AOI-xxxxx | 2022-05-05 | 2022-05-05
Equipment Logic |  | 2022-05-19 | 2022-05-24
| Equipment / Control Module Identification | 2022-05-19 | 2022-05-19
| Equipment -01 | 2022-05-19 | 2022-05-19
| Equipment -02 | 2022-05-19 | 2022-05-19
| Equipment -03 | 2022-05-20 | 2022-05-20
| Equipment -04 | 2022-05-20 | 2022-05-20
| Equipment -05 | 2022-05-23 | 2022-05-23
| Equipment -06 | 2022-05-23 | 2022-05-23
| Equipment -07 | 2022-05-24 | 2022-05-24
| Equipment -08 | 2022-05-24 | 2022-05-24
| Equipment -09 | 2022-05-19 | 2022-05-19
Sequence Logic |  | 2022-05-24 | 2022-05-31
| Sequence -31 | 2022-05-24 | 2022-05-25
| Sequence -32 | 2022-05-26 | 2022-05-27
| Sequence -33 | 2022-05-30 | 2022-05-31
| Sequence -XX | 2022-05-24 | 2022-05-24
| Sequence -XX | 2022-05-24 | 2022-05-24
Main Program |  | 2022-06-01 | 2022-06-05
| Sequence Control | 2022-06-01 | 2022-06-02
| Alarm Logic | 2022-06-02 | 2022-06-02
| Recipe Logic | 2022-06-03 | 2022-06-03
| Setting Logic | 2022-06-04 | 2022-06-04
| Data Log | 2022-06-05 | 2022-06-05
| Dumping Logic | 2022-06-01 | 2022-06-01
HMI Program |  | 2022-05-04 | 2022-06-03
HMI Program- Global Object, Face Plate |  | 2022-05-05 | 2022-05-19
| PopUp - Analog Input | 2022-05-05 | 2022-05-06
| PopUp - Analog Output | 2022-05-09 | 2022-05-10
| PopUp - Pump | 2022-05-13 | 2022-05-13
| PopUp -VentFilter_Faceplate | 2022-05-17 | 2022-05-17
| PopUp - Mode_Selection | 2022-05-19 | 2022-05-19
| PopUp - PID_Faceplate | 2022-05-19 | 2022-05-19
| PopUp - PLC -DI Module | 2022-05-19 | 2022-05-19
| PopUp - PLC - Analog Module | 2022-05-19 | 2022-05-19
| PopUp - XXXXX | 2022-05-05 | 2022-05-05
| PopUp - XXXXX | 2022-05-05 | 2022-05-05
|  | 2022-05-05 | 2022-05-05
|  | 2022-05-05 | 2022-05-05
|  | 2022-05-05 | 2022-05-05
HMI Program Screen |  | 2022-05-20 | 2022-06-03
| Project - Startup Screen | 2022-05-20 | 2022-05-20
| Project - Main Menu | 2022-05-23 | 2022-05-24
| Project - Alarm history | 2022-05-20 | 2022-05-20
| Project - Trend | 2022-05-25 | 2022-05-25
| Project - Parameter | 2022-05-26 | 2022-05-26
| Project - Overview -PWG | 2022-05-27 | 2022-05-27
| Project - Overview -PWSND | 2022-05-28 | 2022-05-28
| Project - Overview -UV | 2022-05-29 | 2022-05-29
| Project - WFISND | 2022-05-30 | 2022-05-30
| Project - System Architecture | 2022-05-31 | 2022-05-31
| Project - OEM Setting | 2022-06-01 | 2022-06-01
| Project - Enduser Setting | 2022-06-02 | 2022-06-02
| Project - Report | 2022-06-03 | 2022-06-03
| Project - Recipe | 2022-05-20 | 2022-05-20
| Project - Overview -05 | 2022-05-20 | 2022-05-20
| Project - Overview -06 | 2022-05-20 | 2022-05-20
| Project - Screen -01 | 2022-05-20 | 2022-05-20
| Project - Screen -02 | 2022-05-20 | 2022-05-20
| Project - Screen -03 | 2022-05-20 | 2022-05-20
| Project - Screen -04 | 2022-05-20 | 2022-05-20
| Project - Screen -05 | 2022-05-20 | 2022-05-20
| Project - Screen -06 | 2022-05-20 | 2022-05-20
| Project - Screen -07 | 2022-05-20 | 2022-05-20
Peporting |  | 2022-05-04 | 2022-05-04
| Reoprt -01 | 2022-05-04 | 2022-05-04
| Reoprt -02 | 2022-05-04 | 2022-05-04
| Reoprt -03 | 2022-05-04 | 2022-05-04
| Reoprt -04 | 2022-05-04 | 2022-05-04
| Reoprt -05 | 2022-05-04 | 2022-05-04
| Reoprt -06 | 2022-05-04 | 2022-05-04
Testing |  | 2022-05-04 | 2022-05-04
| Testing -01 | 2022-05-04 | 2022-05-04
| Testing -02 | 2022-05-04 | 2022-05-04
| Testing -03 | 2022-05-04 | 2022-05-04
| Testing -04 | 2022-05-04 | 2022-05-04
| Testing -05 | 2022-05-04 | 2022-05-04
| Testing -06 | 2022-05-04 | 2022-05-04
Formulas:
Start = MIN([Start, row below]:D16)
Start = MIN([Start, row below])
End = MAX([End, row below]:E16)
End = [Start]

## Activity Project Plan
[13 empty] | Not Started | Not Started | X | X
| Special Events | Start | End |  | Not Started | 26 | [7 empty] | In Progress |  | √
| Time off |  |  |  | In Progress | 1 | [7 empty] | Not required
| Holiday |  |  |  | Not required | 9 | [7 empty] | Completed
[5 empty] | Completed | 24 | [7 empty] | Hold
[5 empty] | Hold | 0
|  | Start | End | % Compl. | Completed Date | Status | Responsibility |  |  | Remark-1 | Remark-2 | Remark-3
Project |  | 2022-05-04 | 2022-06-05 |  |  |  | Rockwell Automation ( Team ) Govind Lathkar Sanjay Panchal | Shrikant ( CN Water ) | Rexcel OTC
Study |  | 2022-05-04 | 2022-05-06 |  |  |  | √ | √
| First Meeting | 2022-05-04 | 2022-05-04 |  |  | Completed |  | √
| FDS Document | 2022-05-04 | 2022-05-04 |  |  | Not required |  | √
| P&I Diagram Standardization | 2022-05-04 | 2022-05-04 |  |  | Completed |  | √ |  | As per CN it is standard
| Master I/O List | 2022-05-05 | 2022-05-06 |  | 2022-05-17 | Completed |  | √
| Equipment Module/Control Module / Phase Identification | 2022-05-05 | 2022-05-06 |  | 2022-05-17 | Completed | √ | √
Documentation - |  | 2022-05-04 | 2022-05-04 |  |  |  |  | √
| FDS | 2022-05-04 | 2022-05-04 |  |  | Not required
Standardisation |  | 2022-05-04 | 2022-05-04
| Nomenclature - ( Controller Program ) | 2022-05-04 | 2022-05-04 |  | 2022-05-17 | Completed | √ | √
| Master I/O List Preparation | 2022-05-04 | 2022-05-04 |  | 2022-05-09 | Completed |  | √
| FDS | 2022-05-04 | 2022-05-04 |  |  | Not required |  | √
| Hardware | 2022-05-04 | 2022-05-04 |  |  | Not Started |  | √
Documentation - Phase / Equipment/ Control Module *1 |  | 2022-05-04 | 2022-05-04
| Sample Development Document- Control Module | 2022-05-04 | 2022-05-04 |  |  | Not required
| Sample Test Document - Control Module | 2022-05-04 | 2022-05-04 |  |  | Not required
Controller Program |  | 2022-05-05 | 2022-06-05
AOI |  | 2022-05-05 | 2022-05-17
| AOI-Analog Input | 2022-05-05 | 2022-05-06 |  |  | Completed | √ |  |  | 1. Shrikant will help Govind for identifying functioanlity
| AOI-Analog Output | 2022-05-09 | 2022-05-10 |  |  | Completed | √ |  |  | 1. Shrikant will help Govind for identifying functioanlity
| AOI-Soft Alarm | 2022-05-11 | 2022-05-11 |  |  | Not required | √ |  |  | 1. Shrikant will help Govind for identifying functioanlity
| AOI-Alarm AOI | 2022-05-12 | 2022-05-12 |  |  | Not required | √ |  |  | 1. Shrikant will help Govind for identifying functioanlity
| AOI-PID AOI | 2022-05-13 | 2022-05-13 |  |  | Completed | √ |  |  | 1. Shrikant will help Govind for identifying functioanlity
| AOI-Pump | 2022-05-16 | 2022-05-16 |  |  | Completed | √ |  |  | 1. Shrikant will help Govind for identifying functioanlity
| AOI-VentFilter | 2022-05-17 | 2022-05-17 |  |  | Not required | √ |  |  | 1. Shrikant will help Govind for identifying functioanlity
| AOI-xxxxx | 2022-05-05 | 2022-05-05 |  |  |  | √ |  |  | 1. Shrikant will help Govind for identifying functioanlity
| AOI-xxxxx | 2022-05-05 | 2022-05-05 |  |  |  | √ |  |  | 1. Shrikant will help Govind for identifying functioanlity
| AOI-xxxxx | 2022-05-05 | 2022-05-05 |  |  |  | √ |  |  | 1. Shrikant will help Govind for identifying functioanlity
Equipment Logic |  | 2022-05-19 | 2022-05-24
| Equipment / Control Module Identification | 2022-05-19 | 2022-05-19 |  | 2022-05-17 | Completed | √ | √
| Equipment -01 | 2022-05-19 | 2022-05-19 |  | 2022-05-17 | Completed | √ | √
| Equipment -02 | 2022-05-19 | 2022-05-19 |  | 2022-05-18 | Completed | √ | √
| Equipment -03 | 2022-05-20 | 2022-05-20 |  | 2022-05-18 | Completed | √ | √
| Equipment -04 | 2022-05-20 | 2022-05-20 |  | 2022-05-18 | Completed | √ | √
| Equipment -05 | 2022-05-23 | 2022-05-23 |  | 2022-05-18 | Completed | √ | √
| Equipment -06 | 2022-05-23 | 2022-05-23 |  | 2022-05-19 | Completed | √ | √
| Equipment -07 | 2022-05-24 | 2022-05-24 |  | 2022-05-19 | Completed | √ | √
| Equipment -08 | 2022-05-24 | 2022-05-24 |  | 2022-05-19 | Completed | √ | √
| Equipment -09 | 2022-05-19 | 2022-05-19 |  | 2022-05-19 | Completed | √ | √
Sequence Logic |  | 2022-05-24 | 2022-05-31
| Sequence -31 | 2022-05-24 | 2022-05-25 |  | 2022-05-20 | In Progress | √ | √ |  | 1, Shrikant and Govind will write logic
| Sequence -32 | 2022-05-26 | 2022-05-27 |  |  | Not Started | √ | √
| Sequence -33 | 2022-05-30 | 2022-05-31 |  |  | Not Started | √ | √
| Sequence -XX | 2022-05-24 | 2022-05-24 |  |  | Not Started
| Sequence -XX | 2022-05-24 | 2022-05-24 |  |  | Not Started
Main Program |  | 2022-06-01 | 2022-06-05
| Sequence Control | 2022-06-01 | 2022-06-02 |  |  | Not Started | √ | √ |  | 1, Shrikant and Govind will write logic
| Alarm Logic | 2022-06-02 | 2022-06-02 |  |  | Not Started | √ | √
| Recipe Logic | 2022-06-03 | 2022-06-03 |  |  | Not Started |  | √
| Setting Logic | 2022-06-04 | 2022-06-04 |  |  | Not Started |  | √
| Data Log | 2022-06-05 | 2022-06-05 |  |  | Not Started |  | √
| Dumping Logic | 2022-06-01 | 2022-06-01 |  |  | Not Started |  | √
HMI Program |  | 2022-05-04 | 2022-06-03
HMI Program- Global Object, Face Plate |  | 2022-05-05 | 2022-05-19
| PopUp - Analog Input | 2022-05-05 | 2022-05-06 |  | 2022-05-18 | Completed | √ |  |  | Shrikant will help Govind finilizer faceplate
| PopUp - Analog Output | 2022-05-09 | 2022-05-10 |  | 2022-05-18 | Completed | √ |  |  | Shrikant will help Govind finilizer faceplate
| PopUp - Pump | 2022-05-13 | 2022-05-13 |  | 2022-05-18 | Completed | √ |  |  | Shrikant will help Govind finilizer faceplate
| PopUp -VentFilter_Faceplate | 2022-05-17 | 2022-05-17 |  |  | Not required | √ |  |  | Shrikant will help Govind finilizer faceplate
| PopUp - Mode_Selection | 2022-05-19 | 2022-05-19 |  |  | Not Started | √ |  |  | Shrikant will help Govind finilizer faceplate
| PopUp - PID_Faceplate | 2022-05-19 | 2022-05-19 |  | 2022-05-18 | Completed | √ |  |  | Shrikant will help Govind finilizer faceplate
| PopUp - PLC -DI Module | 2022-05-19 | 2022-05-19 |  |  | Not Started | √ |  |  | Shrikant will help Govind finilizer faceplate
| PopUp - PLC - Analog Module | 2022-05-19 | 2022-05-19 |  |  | Not Started | √ |  |  | Shrikant will help Govind finilizer faceplate
| PopUp - XXXXX | 2022-05-05 | 2022-05-05
| PopUp - XXXXX | 2022-05-05 | 2022-05-05
| 0 | 2022-05-05 | 2022-05-05
| 0 | 2022-05-05 | 2022-05-05
| 0 | 2022-05-05 | 2022-05-05
HMI Program Screen |  | 2022-05-20 | 2022-06-03
| Project - Startup Screen | 2022-05-20 | 2022-05-20 |  |  | Not Started |  | √ |  | Shrikant will help Govind finilizer faceplate
| Project - Main Menu | 2022-05-23 | 2022-05-24 |  |  | Not Started |  | √ |  | Shrikant will help Govind finilizer faceplate
| Project - Alarm history | 2022-05-20 | 2022-05-20 |  |  | Not Started |  | √ |  | Shrikant will help Govind finilizer faceplate
| Project - Trend | 2022-05-25 | 2022-05-25 |  |  | Not Started |  | √ |  | Shrikant will help Govind finilizer faceplate
| Project - Parameter | 2022-05-26 | 2022-05-26 |  |  | Not Started |  | √ |  | Shrikant will help Govind finilizer faceplate
| Project - Overview -PWG | 2022-05-27 | 2022-05-27 |  |  | Not Started |  | √ |  | Shrikant will help Govind finilizer faceplate
| Project - Overview -PWSND | 2022-05-28 | 2022-05-28 |  |  | Not Started |  | √ |  | Shrikant will help Govind finilizer faceplate
| Project - Overview -UV | 2022-05-29 | 2022-05-29 |  |  | Not Started |  | √ |  | Shrikant will help Govind finilizer faceplate
| Project - WFISND | 2022-05-30 | 2022-05-30 |  |  | Not Started |  | √ |  | Shrikant will help Govind finilizer faceplate
| Project - System Architecture | 2022-05-31 | 2022-05-31 |  |  | Not Started |  | √ |  | Shrikant will help Govind finilizer faceplate
| Project - OEM Setting | 2022-06-01 | 2022-06-01 |  |  | Not Started |  | √ |  | Shrikant will help Govind finilizer faceplate
| Project - Enduser Setting | 2022-06-02 | 2022-06-02 |  |  | Not Started |  | √ |  | Shrikant will help Govind finilizer faceplate
| Project - Report | 2022-06-03 | 2022-06-03
| Project - Recipe | 2022-05-20 | 2022-05-20
| Project - Overview -05 | 2022-05-20 | 2022-05-20
| Project - Overview -06 | 2022-05-20 | 2022-05-20
| Project - Screen -01 | 2022-05-20 | 2022-05-20
| Project - Screen -02 | 2022-05-20 | 2022-05-20
| Project - Screen -03 | 2022-05-20 | 2022-05-20
| Project - Screen -04 | 2022-05-20 | 2022-05-20
| Project - Screen -05 | 2022-05-20 | 2022-05-20
| Project - Screen -06 | 2022-05-20 | 2022-05-20
| Project - Screen -07 | 2022-05-20 | 2022-05-20
Peporting |  | 2022-05-04 | 2022-05-04
| Reoprt -01 | 2022-05-04 | 2022-05-04
| Reoprt -02 | 2022-05-04 | 2022-05-04
| Reoprt -03 | 2022-05-04 | 2022-05-04
| Reoprt -04 | 2022-05-04 | 2022-05-04
| Reoprt -05 | 2022-05-04 | 2022-05-04
| Reoprt -06 | 2022-05-04 | 2022-05-04
Testing |  | 2022-05-04 | 2022-05-04
| Testing -01 | 2022-05-04 | 2022-05-04
| Testing -02 | 2022-05-04 | 2022-05-04
| Testing -03 | 2022-05-04 | 2022-05-04
| Testing -04 | 2022-05-04 | 2022-05-04
| Testing -05 | 2022-05-04 | 2022-05-04
| Testing -06 | 2022-05-04 | 2022-05-04
Formulas:
Start = MIN([Start, row below]:D16)
Start = MIN([Start, row below])
End = MAX([End, row below]:E16)
End = MAX([End, row below]:[End, row below])

## Activity Chart
|  | No of Days | [7 empty] | Data2
| Govind Lathkar | 0
| Rexcel OTC | 1
| Shrikant | 0
| Total | 1
|  |  |  | 0 | 0 | 1
Sr. No. | Date | Place | Activity | Govind Lathkar | Rexcel OTC | Shrikant | Remark
1 | 2021-05-12 | CN Water -(Site ) | 1 . Docudtoinasfd asdfasdfasdf 2. asdfasdf |  |  | Yes |  | No | Yes
2 |  | CN Water - | [6 empty] | No
CN Water -(Site )
[8 empty] | CN Water - | CN Water -
Rockwell Office
Rexcel Office
Other Place..
Meeting with German Consultant Klaus

## Memory Calculation
Cpu Memory | 1000 | Tobe Used % | 70
Sr. No | Cpu Memory ( in Byte) | Tobe Used ( In Byte ) | Used Memory ( In Byte ) | Remain ( In Byte ) | Remain ( In Kb ) | In % | Remark | Kb | %
1 | 1024000 | 716800 | 161280 | 555520 | 542.5 | 77.5 | After Adding Modules
2 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | -157.5 | -22.5
3 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
4 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
5 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
6 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
7 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
8 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
9 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
10 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
11 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
12 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
13 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
14 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
15 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
16 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
17 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
18 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
19 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
20 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
21 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
22 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
23 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
24 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
25 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
26 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
27 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
28 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
29 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
30 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
31 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
32 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
33 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
34 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
35 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
36 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
37 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
38 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
39 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
40 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
41 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
42 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
43 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
44 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
45 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
46 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
47 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
48 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
49 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
50 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
51 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
52 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
53 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
54 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
55 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
56 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
57 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
58 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
59 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
60 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
61 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
62 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
63 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
64 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
65 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
66 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
67 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
68 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
69 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
70 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
71 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
72 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
73 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
74 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
75 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0
76 | 1024000 | 716800 |  | 716800 | 700 | 100 |  | 0 | 0

## BOM
|  |  |  | 88 | 41 | 3 | 0
Sr. No | Catalog # | Description | Qty | DI | D0 | AI | AO
1 | 1769-L19ER-BB1B | CompactLogix 5370 L1 Controller, 2 EtherNet/IP ports, 1Mb memory, 16 DC in, 16 DC out, up to 8 1734 I/O expansion modules. | 1 | 16 | 16
2 | 1734-OE4C | 4-Point Analog Current Output Module (Preferred Availability) | 1 |  |  |  | 4
3 | 1734-IB4 | 24V DC 4-Point Sink Input Module (Preferred Availability) | 1 |  |  | 4
4 | 1734-IE8C | 8-Channel High-Density Analog Current Input Module (Preferred Availability) | 2
5 | 1734-OB8 | 24V DC 8-Point Source Output Module (Preferred Availability) | 2 |  | 16
6 | 1734-TOP | One-Piece Terminal Base, 8-point, Screw Clamp Terminals (Preferred Availability) | 6
7 | 2711P-T7C21D8S | Graphic Terminal,Standard Model,6.5 in. Display, TFT Color,Touch Screen,Single Ethernet,18-30 V DC (Preferred Availability) | 1
8 | 9701-VWSB100AENM | MEDIA - FactoryTalk View SE Station 100 Display (ENGLISH) | 1
9 | 1783-US5T | Stratix 2000 Switch, Unmanaged, 5 Copper Ports (Preferred Availability) | 1
Total |  |  |  | 16 | 32 | 4 | 4